## Timeline
Weeknum | Weekday | Date | Task | Research Project | Description
38 | Thursday | 2024-09-19 | Revisit Draft | MS-NNS
38 | Friday | 2024-09-20 | Revisit Draft | MS-NNS
38 | Saturday | 2024-09-21 | Revisit Draft | MS-NNS
38 | Sunday | 2024-09-22 | Revisit Draft | MS-NNS
39 | Monday | 2024-09-23 | Revisit Draft | MS-NNS
39 | Tuesday | 2024-09-24 | Revisit Draft | MS-NNS
39 | Wednesday | 2024-09-25 | Revisit Draft | MS-NNS
39 | Thursday | 2024-09-26 | Revisit Draft | MS-NNS
39 | Friday | 2024-09-27 | Revisit Draft | MS-NNS
39 | Saturday | 2024-09-28 | Revisit Draft | MS-NNS
39 | Sunday | 2024-09-29 | Run Simulation Analysis | MS-NNS
40 | Monday | 2024-09-30 | Run Simulation Analysis | MS-NNS
40 | Tuesday | 2024-10-01 | Run Simulation Analysis | MS-NNS
40 | Wednesday | 2024-10-02 | Run Simulation Analysis | MS-NNS
40 | Thursday | 2024-10-03 | Run Simulation Analysis | MS-NNS
40 | Friday | 2024-10-04 | Run Simulation Analysis | MS-NNS
40 | Saturday | 2024-10-05 | Run Simulation Analysis | MS-NNS
40 | Sunday | 2024-10-06 | Run Simulation Analysis | MS-NNS
41 | Monday | 2024-10-07 | Revise Simulation Analysis | MS-NNS
41 | Tuesday | 2024-10-08 | Revise Simulation Analysis | MS-NNS
41 | Wednesday | 2024-10-09 | Revise Simulation Analysis | MS-NNS
41 | Thursday | 2024-10-10 | Revise Simulation Analysis | MS-NNS
41 | Friday | 2024-10-11 | Revise Simulation Analysis | MS-NNS
41 | Saturday | 2024-10-12 | Draft First Manuscript | MS-NNS
41 | Sunday | 2024-10-13 | Draft First Manuscript | MS-NNS
42 | Monday | 2024-10-14 | Draft First Manuscript | MS-NNS
42 | Tuesday | 2024-10-15 | Draft First Manuscript | MS-NNS
42 | Wednesday | 2024-10-16 | Draft First Manuscript | MS-NNS
42 | Thursday | 2024-10-17 | Revise Manuscript | MS-NNS
42 | Friday | 2024-10-18 | Revise Manuscript | MS-NNS
42 | Saturday | 2024-10-19 | Revise Manuscript | MS-NNS
42 | Sunday | 2024-10-20 | Revise Manuscript | MS-NNS
43 | Monday | 2024-10-21 | Revise Manuscript | MS-NNS
43 | Tuesday | 2024-10-22 | Revise Manuscript | MS-NNS
43 | Wednesday | 2024-10-23 | Revise Manuscript | MS-NNS
43 | Thursday | 2024-10-24 | Revise Manuscript | MS-NNS
43 | Friday | 2024-10-25 | Revise Manuscript | MS-NNS
43 | Saturday | 2024-10-26 | Revise Manuscript | MS-NNS
43 | Sunday | 2024-10-27 | Revise Manuscript | MS-NNS
44 | Monday | 2024-10-28 | Revise Manuscript | MS-NNS
44 | Tuesday | 2024-10-29 | Revise Manuscript | MS-NNS
44 | Wednesday | 2024-10-30 | Revise Manuscript | MS-NNS
44 | Thursday | 2024-10-31 | Submit to the journal | MS-NNS
44 | Friday | 2024-11-01 | Submit to the journal | MS-NNS
44 | Saturday | 2024-11-02 | Initial Discussion with Co-authors | MS-RFS-P
44 | Sunday | 2024-11-03 | Initial Discussion with Co-authors | MS-RFS-P
45 | Monday | 2024-11-04 | Initial Discussion with Co-authors | MS-RFS-P
45 | Tuesday | 2024-11-05 | Initial Discussion with Co-authors | MS-RFS-P
45 | Wednesday | 2024-11-06 | Initial Discussion with Co-authors | MS-RFS-P
45 | Thursday | 2024-11-07 | Run Simulation Analysis | MS-RFS-P
45 | Friday | 2024-11-08 | Run Simulation Analysis | MS-RFS-P
45 | Saturday | 2024-11-09 | Run Simulation Analysis | MS-RFS-P
45 | Sunday | 2024-11-10 | Run Simulation Analysis | MS-RFS-P
46 | Monday | 2024-11-11 | Run Simulation Analysis | MS-RFS-P
46 | Tuesday | 2024-11-12 | Run Simulation Analysis | MS-RFS-P
46 | Wednesday | 2024-11-13 | Run Simulation Analysis | MS-RFS-P
46 | Thursday | 2024-11-14 | Run Simulation Analysis | MS-RFS-P
46 | Friday | 2024-11-15 | Run Simulation Analysis | MS-RFS-P
46 | Saturday | 2024-11-16 | Revise Simulation Analysis | MS-RFS-P
46 | Sunday | 2024-11-17 | Revise Simulation Analysis | MS-RFS-P
47 | Monday | 2024-11-18 | Revise Simulation Analysis | MS-RFS-P
47 | Tuesday | 2024-11-19 | Revise Simulation Analysis | MS-RFS-P
47 | Wednesday | 2024-11-20 | Revise Simulation Analysis | MS-RFS-P
47 | Thursday | 2024-11-21 | Revise Simulation Analysis | MS-RFS-P
47 | Friday | 2024-11-22 | Revise Simulation Analysis | MS-RFS-P
47 | Saturday | 2024-11-23 | Draft First Manuscript | MS-RFS-P
47 | Sunday | 2024-11-24 | Draft First Manuscript | MS-RFS-P
48 | Monday | 2024-11-25 | Draft First Manuscript | MS-RFS-P
48 | Tuesday | 2024-11-26 | Draft First Manuscript | MS-RFS-P
48 | Wednesday | 2024-11-27 | Draft First Manuscript | MS-RFS-P
48 | Thursday | 2024-11-28 | Draft First Manuscript | MS-RFS-P
48 | Friday | 2024-11-29 | Draft First Manuscript | MS-RFS-P
48 | Saturday | 2024-11-30 | Draft First Manuscript | MS-RFS-P
48 | Sunday | 2024-12-01 | Draft First Manuscript | MS-RFS-P
49 | Monday | 2024-12-02 | Revise Manuscript | MS-RFS-P
49 | Tuesday | 2024-12-03 | Revise Manuscript | MS-RFS-P
49 | Wednesday | 2024-12-04 | Revise Manuscript | MS-RFS-P
49 | Thursday | 2024-12-05 | Revise Manuscript | MS-RFS-P
49 | Friday | 2024-12-06 | Revise Manuscript | MS-RFS-P
49 | Saturday | 2024-12-07 | Revise Manuscript | MS-RFS-P
49 | Sunday | 2024-12-08 | Revise Manuscript | MS-RFS-P
50 | Monday | 2024-12-09 | Revise Manuscript | MS-RFS-P
50 | Tuesday | 2024-12-10 | Revise Manuscript | MS-RFS-P
50 | Wednesday | 2024-12-11 | Revise Manuscript | MS-RFS-P
50 | Thursday | 2024-12-12 | Revise Manuscript | MS-RFS-P
50 | Friday | 2024-12-13 | Submit to the journal | MS-RFS-P
50 | Saturday | 2024-12-14 | Submit to the journal | MS-RFS-P
50 | Monday | 2024-12-09 | Final Exam | Academic Calendar
50 | Tuesday | 2024-12-10 | Final Exam | Academic Calendar
50 | Wednesday | 2024-12-11 | Final Exam | Academic Calendar
50 | Thursday | 2024-12-12 | Final Exam | Academic Calendar
50 | Friday | 2024-12-13 | Final Exam | Academic Calendar
50 | Sunday | 2024-12-15 | Christmas holiday | Holiday
51 | Monday | 2024-12-16 | Christmas holiday | Holiday
51 | Tuesday | 2024-12-17 | Christmas holiday | Holiday
51 | Wednesday | 2024-12-18 | Christmas holiday | Holiday
51 | Thursday | 2024-12-19 | Christmas holiday | Holiday
51 | Friday | 2024-12-20 | Christmas holiday | Holiday
51 | Saturday | 2024-12-21 | Christmas holiday | Holiday
51 | Sunday | 2024-12-22 | Christmas holiday | Holiday
52 | Monday | 2024-12-23 | Christmas holiday | Holiday
52 | Tuesday | 2024-12-24 | Christmas holiday | Holiday
52 | Wednesday | 2024-12-25 | Christmas holiday | Holiday
52 | Thursday | 2024-12-26 | Christmas holiday | Holiday
52 | Friday | 2024-12-27 | Christmas holiday | Holiday
52 | Saturday | 2024-12-28 | Christmas holiday | Holiday
52 | Sunday | 2024-12-29 | Christmas holiday | Holiday
53 | Monday | 2024-12-30 | Christmas holiday | Holiday
53 | Tuesday | 2024-12-31 | Christmas holiday | Holiday
1 | Wednesday | 2025-01-01 | Christmas holiday | Holiday
48 | Wednesday | 2024-11-27 | Thanksgiving Break | Holiday
48 | Thursday | 2024-11-28 | Thanksgiving Break | Holiday
48 | Friday | 2024-11-29 | Thanksgiving Break | Holiday
42 | Monday | 2024-10-14 | Fall Break | Holiday
42 | Tuesday | 2024-10-15 | Fall Break | Holiday
1 | Thursday | 2025-01-02 | 2025 Spring Classes Begin | Academic Calendar
1 | Friday | 2025-01-03 | 2025 Spring Classes Begin | Academic Calendar
Formulas:
Weeknum = WEEKNUM(Table4[[#This Row],[Date]],2)
Weeknum = WEEKNUM([Date],2)

## Project_Dictionary
Label | FullName | First Author
MS-MNA | Methodological Study of Missingness of Network Analysis | AQ
ES-MAD | Empirical Study of Missingness method in Acceralation Data | AQ
MS-NNS | Methodological Study of Novel Network Score | JZ
MS-RFS-P | Methodological Study of Rating Factor Score (Paper) | JZ
MS-NAR | Methodological Study of Network Analysis Reliability (Spencer) | JZ
MS-RFS-C | Methodological Study of Rating Factor Score (Conference) | LJ
PD-SGD | Program Development of ShinyApp of SEM of Gene Data | ZJ